## Slide 1
Engineering Management
Construction Management and Accounts: N. L. Pandy.
Project Management with CPM, PERT, and Precedence Diagramming, 3rd Edition, by Moder J., Phillips, C., and Davis, E.
Construction Management: Daniel W. Halpin.
Construction Project Management Handbook : Federal Transit Administration.
Dr. Ola Adel
Ph.D Structural Engineering
Al-Mansour University College
كلية المنصور الجامعة
Civil Engineering Department
Third Year 2017-2018
**Engineering management**

## Slide 2
Lecture-4-

## Slide 3
Activity |  | Duration (day) | Predecessor | Successor | direct costs $ | indirect costs $ for every 5 days
Site clearing (of brush and minor debris), | A | 5 | -- | C,D | 50000 | 5000
Removal of trees, | B | 12 | -- | E,F | 60000 | 5000
General excavation, | C | 7 | A | G | 70000 | 5000
Grading general area, | D | 9 | A | E | 90000 | 5000
Excavation for utility trenches. | E | 14 | D, B | H, I | 70000 | 5000
Placing formwork and reinforcement for concrete, | F | 18 | B | I | 90000 | 5000
Installing sewer lines, | G | 11 | C | H | 110000 | 5000
Installing other utilities | H | 13 | E, G | -- | 130000 | 5000
Pouring concrete. | I | 15 | E, F | -- | 150000 | 5000
Example 1

## Slide 4
10
20
30
A
B
5
12
40
C
7
50
D
9

## Slide 5
10
20
30
A
B
5
12
40
C
7
D
9
30
E
14

## Slide 6
10
20
30
A
B
5
12
40
C
7
50
D
9
60
E
14
70
F
18
0
dummy
80
G
11

## Slide 7
10
20
30
A
B
5
12
40
C
7
50
D
9
80
E
14
70
F
18
0
dummy
60
G
11
H
13
0
dummy
80
I
15

## Slide 8
10
20
30
A
B
5
12
40
C
7
50
D
9
80
E
14
70
F
18
0
dummy
60
G
11
H
13
0
dummy
I
15
28
45
12
30
12
5
0
12
14
23
28
41

## Slide 9
10
20
30
A
B
5
12
40
C
7
50
D
9
80
E
14
70
F
18
0
dummy
60
G
11
H
13
0
dummy
I
15
45
30
32
12
16
19
12
0
2
30
16
7

## Slide 10
10
20
30
A
B
5
12
40
C
7
50
D
9
80
E
14
70
F
18
0
Dummy 1
60
G
11
H
13
0
Dummy 2
I
15
28
45
12
30
12
5
0
12
14
23
28
41
45
30
32
12
16
19
0
2
30
16
12
7
A-O-A Network

## Slide 11
A-C-G-H=5+7+11+13=36
A-C-G-dummy-J=5+7+11+0+15=38
B-dummy-E-H=12+0+14+13=29
A-D-E-H=5+9+14+13=41
A-D-E-dummy-I=5+9+14+0+15=43
B-F-I=12+18+15=45 longest path=critical path ………Tf=0

## Slide 13
10
20
A=name
Duration=5
Et
Eh
Lt
Lh
Free float
Total float
Total float=Lh-d-Et
Free float=Eh-d-Et

## Slide 14
Activity | Duration (day) | Et | Eh | Lt | Lh | Early |  | Late |  | Total float | Free float
 |  |  |  |  |  | start | finish | start | finish |  | 
A | 5 | 0 | 5 | 0 | 7 | 0 | 5 | 2 | 7 | 2 | 0
B | 12 | 0 | 12 | 0 | 12 | 0 | 12 | 0 | 12 | 0 | 0
C | 7 | 5 | 12 | 7 | 19 | 5 | 12 | 12 | 19 | 7 | 0
D | 9 | 5 | 14 | 7 | 16 | 5 | 14 | 7 | 16 | 2 | 0
E | 14 | 14 | 28 | 16 | 30 | 14 | 28 | 16 | 30 | 2 | 0
F | 18 | 12 | 30 | 12 | 30 | 12 | 30 | 12 | 30 | 0 | 0
G | 11 | 12 | 28 | 19 | 30 | 12 | 23-28 | 19 | 30 | 7 | 5
H | 13 | 28 | 45 | 30 | 45 | 28 | 41-45 | 32 | 45 | 4 | 4
I | 15 | 30 | 45 | 30 | 45 | 30 | 45 | 30 | 45 | 0 | 0
Dummy 1 | 0 | 12 | 14 | 12 | 16 | 12 | 12-14 | 16 | 16 | 4 | 2
Dummy 2 | 0 | 28 | 30 | 30 | 30 | 28 | 28-30 | 30 | 30 | 2 | 2

## Slide 15
A-O-N Network
Start
A
B
C
D
E
F
G
H
I
End

## Slide 16
Linear Projects نموذج

## Slide 17
Gant Chart

## Slide 18
Cash flow-Gant Chart ..calculate the money for every 5 days and add the indirect cost

## Slide 20
Program Gant Chart

## Slide 21
Program A-O-N

## Slide 22
Activity code | Duration | Activity that Preceded
A | 5 | --
B | 10 | A
C | 8 | A
D | 7 | B
E | 12 | C
F | 6 | C,D
G | 4 | E,F
Example 2

## Slide 25
A-O-N

## Slide 26
A-O-A