## Slide 1
Engineering Management
Construction Management and Accounts: N. L. Pandy.
Project Management with CPM, PERT, and Precedence Diagramming, 3rd Edition, by Moder J., Phillips, C., and Davis, E.
Construction Management: Daniel W. Halpin.
Construction Project Management Handbook : Federal Transit Administration.
Dr. Ola Adel
Ph.D Structural Engineering
Al-Mansour University College
كلية المنصور الجامعة
Civil Engineering Department
Third Year 2017-2018
**Engineering management**

## Slide 2
Lecture-5-2

## Slide 3
Activity code | Duration | Activity that Preceded
A | 2 | --
B | 3 | --
C | 3 | --
D | 6 | C
E | 4 | A,B
F | 2 | A
G | 4 | F, D
H | 3 | E, F, D
I | 2 | D
J | 3 | G
K | 4 | I, J
Example
Draw A-O-A networks for the following activities in the schedule table below and using the duration of activities to find the Earliest event and Latest Event, then determine the floats table and identify the critical activities in table and drawing.